## Sheet1
Logout link in the user icon | Done | P#1
Popup scroling issue in timesheet popup | Done | P#1
export timesheet xlsx format issue | Done | P#1
edit fields issue in timesheet popup | Done | P#1
space between arrows and top, bottom top 60%, bottom 40% | Done | P#1
Change password in header | Done | P#1
Show dates to current dates in timesheet loader | Done | P#1
Remove Hard coding for fte current, last and previous month header | Done | P#1
DashBoard |  | P#1
Retain "Vendors", "# of Consultants" and "Time Sheets" | Done | P#1
Remove "Avg Retention", "Invoices", "Payments", "Remaining PO Value" | Done | P#1
Better show Static Data only; Dynamic data update is not feasible | Done | P#1
Should display data in alignment with the current financial year (July - June) | ND | P#1
Timesheet |  | P#2
Tool will generate time sheets at the end of the month and should be shared to hiring managers for approval | Done | P#2
Need to capture time stamp in which each of the time sheet was approved by hiring managers | Done | P#2
Procurement should have an option to check if the time sheet approvals were done according to pre-set deadline and should have option to escalate if not done on time. | Done | P#2
Need to have a tab to indicate "Approved vs Pending Approvals" | Done | P#2
Login hours *** To be computed based on the system usage and productive hours ** To consider if the work is being done from "Office" or using "VPN" (work from home) ** Should have option to integrate data from current VPN (GlobalProtect) ***To figure out and list all the applications being active while working from home *** System standby time to be computed only if the system is idle for more than half-an-hour (need to have option to configure) | ND | P#2
Vendors
No attachments required | Done | P#1 | Aditya
Need to have option to choose "Yes/No" against the business engagement documents like MSA & NDA | Done | P#1 | Aditya
If a listed Vendor is selected, a bigger window should pop up displaying the complete information about the vendor (this can include consultants, performance metrics, or any other relevant data that needs to be referred to against each vendor) | Done | P#1 | Aditya
Consultants |  | P#1
Add a column to indicate "Current Experience" | Done | P#1 | Aditya
Add a column to indicate "Experience in WD" | Done | P#1 | Aditya
Remove "Amount Left" option (not relevant) | Done | P#1 | Aditya
Replace "Delete" option with "Active/In-Active" option | Done | P#1 | Aditya
For setting a particular consultant as inactive, managers should have an option to enter free text explaining the reason for setting as inactive, also should have LWD captured for further reference | Done | P#1 | Aditya
All In-Active consultants should be listed together in a separate bucket for future reference. | Done | P#1 | Aditya
Consultants to have login credentials to Apply Leaves; This should be seen by Hiring Managers and enable them for Approvals and the same to be considered for capturing leave data on "Time Sheets" | Done | P#1
Add Consultant |  | P#1
Need to have option to upload "Qualification Certificates" along with "BGV" and "Resume" | Done | P#1
Replace "Validity" with "Comments" and enable free text entry to add more details about the consultant | Done | P#1
Band change |  | P#2
Should indicate about the consultants whos band change needs to be done in near future (60 days in advance) | Done | P#2 | Aditya
Band change to be consider as per financial year (July to June) | ND | P#2 | Aditya
< 6 months to be in Previous Lesser Slab and > 6 months to be in Next Higher Slab | Done | P#2 | Aditya
Reports |  | P#3
Option to be added to have reports specific to vendors or consultants | ND | P#3
To include % of attrition with each vendor (this can be an input for HBR discussions) | ND | P#3
Access Control |  | P#2
A Super User credential to be created; | Done | P#2
Needs to have provision to enable/toggle access control to managers and other parties based on relevance | Done | P#2
Hiring Managers should have access to share Approvals | Done | P#2
Notifications |  | P#2
Need to have option to send email to take relevant pending actions | Done | P#2
Also should have options to send escalation emails | Done | P#2
Show current month timesheet in ftes page(no need of previous month) | Done | P#1
Approve button in current month if last day of month and for previous month | Done | P#2
idle time configuration in admin panel | Done | P#1
detect loggedin from VPN or not | ND | P#2
Make bell icon for notification instead of text | Done | P#2
show count of new notifications | Done | P#2
show notification popup down of the bell icon | Done | P#2
alignment issue in add contractor | Done | P#1
leaves adding functionality | Done | P#1
bgv text in add contractors page | Done | P#1
Contractor login land in leaves page no access for other pages | Done | P#1
Changes on 16-12-2019 | By Subodh
change subject to Action: or Escalation: for notification mail popup | Done
Add icons for email text for notification popup | Done
Approved in smaller font size in fte timesheet page | Done
Approve buttton should be like icon | Done
Summary should be on top of the timesheet popup | Done
if clicked on save button the textbox shuld be readonly if clicked on edit then textbox should editable | Done
search section first company name and status in contractors page | Done
make google like functionality for vendor text box | Done
calendar has to open automatically in leave application popup | Done
if leave is not approved has to take comments text in leaves page | Done
leave status should be pending, approved and not approved | Done
If new leave added should show in the notification section | Done
dashboard top summary should only for admin of VMO | Done
form label and field are in the same line | Done
changing consultant from active to inactive should reflect in the notification section | Done
notification icon should be on top right side of header. | Done
Discussion on 20-12-2019(changes by ranganath and aravind)
Change to working days instead of working hours | Done
createria for managers to accept timesheet for range in less hours | ND
remove leave hours from total hours | Done
show the days instead of hours in fte list page | Done
change text to overall exp in place of current experience | Done
instead of last month use previous month text in fte list page | Done
month start send auto mail to hiring managers for timesheets | ND
send folloup messages to second and third for admins cc and hiring managers | ND
hiring /reporting managers in consultants | Done
leave reason has to know for leave 1)wfh 2)training 3)customer visit 4)travel 5)offsite 6)others (reason mandatory for others) | ND
change leaves to LMS | Done